## PROPOSAL
PROJECT NAME | Grass Pump Dispenser with ROS (Robotics Operating System) & HMI
JOB LOCATION | Zapopan, Jalisco
EST. START DATE | 2024-11-22 | EST. END DATE | 2025-01-02
PROJECT LEADER | Ing. Moises Romo Corona 🤖 | CLIENT COMPANY | Relant
PHONE | 3310826184 | ADDRESS | Abetos 521 Colonia Los Pinos, CP 45120, Zapopan, Jalisco, México
EMAIL | jm.roco@gmail.com
SUMMARY | Automate a grass dispense pump, where the control logic is running under ROS nodes. The status of actuators and sensors will be displayed into an HMI. The main communication protocol between ROS nodes and Master control devices will be TCP Modbus.
DESIRED DELIVERIES | 1) ROS2 control code, included Master Node and HMI node (git hub repository access and ownership by Relant) (do not include the UI design, only the register communication) 2) ROS 2 Humble setup and configuration under Ubuntu 24.04 3) Knowledge transfer with the team about ROS and coding
BENEFITS OF PROJECT | Prepare the baseline of software and hardware to make ROS to Control dispenser pumps and other devices
PROJECT TEAM | Ing. Elias Méndez Ing. Moisé Romo Ing. Francisco Ivañez
PHASES OF WORK | 1) Proof of concept with ROS (Moises, done) 2) Design (Moises, see schematics sheet) 3) Define master control logic (Relant) 4) Provide hardware for testing and connect devices (Relant) 5) Provide hardware to run ROS (Relant) 6) Install and configure ROS + PiTunnel (Moises) - run under secure user - disable not required OS services - add copyright 7) ROS nodes development (Moises) 8) Install and run ROS nodes (Moises) 9) Test Master control ROS Node with hardware (Moises & Relant) 10) Test HMI ROS Node with hardware (Moises & Relant) 11) Test control logic + HMI user interaction (Moises & Relant) 12) Sign off | OBSERVATIONS | After project completion, This proposal Includes 3 hrs of remote support using PiTunnel (license provided by Relant) Any extra work hour after project Completion support will have a Cost of 1,000 MXN
ESTIMATED WORK HOURS | 10 HRS
PROPOSAL MAY BE DECLINED IF NOT ACCEPTED BY: |  | 2024-11-21
ESTIMATED COST | 35,000 MXN + IVA * this is subject to final control complexity, but this is the estimated cost
AUTHORIZED BY